## Slide 1: Linux Kernel Capability
Kickoff Meeting on 10-11-2017

## Slide 2: Project Details
Project Type: | Capability
Project Classification: | Development
Client Details: | NA
Customer Representative: | NA
Engagement Model: | NA

## Slide 3: Scope and Objectives
Scope includes development of modules for the Linux OS kernel, device drivers, applications for the Linux Embedded platform Modules from ongoing customer and internal solution project will be assigned
Objectives are as follows Gain hand-on on Linux kernel basic programing including Device Driver for various peripherals, functional testing, debugging. Understanding GES work flow process Gain understanding of GES project tools such as svn, static analyzer, bug tracker tools etc At the end of completion of this capability project engineer must be able to implement device driver and kernel module on Linux and be able to clear customer interviews for Linux based driver requirements

## Slide 4: Overview and Architecture or System Diagram

## Slide 5: Team ,Roles & Responsibilities and intergroup coordination, Skills and Gaps
SL. No | Name | Role | Responsibility | Skills | Gaps
1 | Abhijith | PM | Project Management |  | NA
2 | Mahesh K | STL | Technical | C, Linux Drivers | NA
3 | C M Naveen Kumar Reddy | SE | Development, Testing | C, Linux Fundamentals | Linux Drivers and various OS components.
4 | Tatikonda Venkata Rao | SE | Development, Testing | C, Linux Fundamentals | Linux Drivers and various OS components.
5 | Kalasariya Ravidra Jivanbhai | SE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.
6 | Saurabh Kumar | SSE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.

## Slide 6: Team ,Roles & Responsibilities and intergroup coordination, Skills and Gaps
SL. No | Name | Role | Responsibility | Skills | Gaps
7 | Pankaj Kumar | SE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.
8 | Kalva Prasanna Kumar | SE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.
9 | G Sarathbabu Naidu | SE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.
10 | Dakshiraju Naresh | SE | Development, Testing | C, Linux Fundamentals | Linux Driver and various components.
11 | Rajendra D | QA | SQA coordinator | C, Linux Fundamentals | Linux Driver and various components.

## Slide 7: Estimation Details
Estimated Effort | 2.5 Months
Estimated Size | 8
Estimated Schedule in calendar months | 2.5 Months
Expected Start Date | 10-Nov-17
Expected Completion Date | 18-Jan-18

## Slide 8: Milestones
Sl.No | Milestone | Target Date
1 | ARM presentations | 14-11-17
2 | Linux Driver basic presentation | 16-11-17
3 | Environment setup and various boot options like tftp, nfs, mmc, uart, cross compilation. | 20-11-17
4 | Linux pseudo code Character driver and app ,unit and functional testing | 27-11-17
5 | Linux pseudo code block driver and app ,unit and functional testing | 5-12-17
6 | Kgdb | 13-12-17
7 | Kernel mem leak and profiling tools, static analyzer tools. | 21-12-17
8 | Actual drivers | 18-01-18

## Slide 9: Resource requirement
 |  |  |  | Required Duration | 
Department |  |  | Current Availability /Req | Start date/Target date | End date
System Admin | Hardware Requirement |  |  |  | 
 | 1 | Beaglebone /RPI | yes | 10-11-17 | 18-01-18
 | 2 |  |  |  | 
 | Software Requirement |  |  |  | 
 | 1 | Linux source | yes | 10-11-17 | 18-01-18
 | 2 |  |  |  | 
 | Access permission |  |  |  | 
 | 1 | SVN (need to create) | No | 10-11-17 | 18-01-18
 | 2 | Gitlab(need to create) | No | 10-11-17 | 18-01-18

## Slide 10: Resource requirement
 |  |  |  | Required Duration | 
HR | Resource Requirement |  |  |  | 
 | 1 | SSE | 1 | 10-11-17 | 18-01-18
 | 2 | SE | 7 | 10-11-17 | 18-01-18
 | 3 | TE |  |  | 18-01-18
 | 4 | PL/STL | 1 | 10-11-17 | 18-01-18
Quality | 1 | Audit requirements | 1 | 10-11-17 | 18-01-18
 | 2 | Standards |  | 10-11-17 | 18-01-18
 | 3 | Tailoring, Deviation |  | 10-11-17 | 18-01-18

## Slide 11: Resource requirement
Administration | 1 | Statutory Compliances for items received |  |  | 
 | 2 | Security of supplied hardware |  |  | 
Training | 1 | Technical Training Requirements | C, ARM, Device Drivers, Debugging Techniques | on job training | 
 | 2 | Tools Training Requirements | SVN, GIT, Hardware handling |  | 
 | 3 | Process Training Requirements | GES Project Workflow , IP Security |  | 

## Slide 12: Project Management Expectations
  Deliverables
    Source Codes, Bring up guides, Test results
  Documents
    Project workbook, SPP, GES Sprint Sheet, HLD, LLD, Code, Test reports
  Records
    Meeting MOMs, Process Compliance check Forms, Weekly Status Reports, Management Approvals etc.,
  SDLC Model
    Agile
  Project Monitoring and tracking
    Sprint sheet
  Project Progress Reviews
    Weekly status report and monthly meeting
    Timesheet maintained in Sprint sheet
    Project Monitoring Records
  Escalation – Responsibility
    SE/SSE -> ML -> TL -> PL -> PM -> PH

## Slide 13: Review Plan and Defect Prevention Plan
  Review Plan
    SPP Reviews, SQA Reviews
    SRS review (requirements will be part of Sprint sheet)
    HLD review
    Code review
    Test Case review
    Responsibility for SQA Reviews, PM Reviews and Senior Management Reviews with Target date
  Defect Prevention Plan
    Refer to the Organization’s DP Database.

## Slide 14: Initial Risks Identified (if any)
Risks Identified | Probability | Severity | Impact | Contingency/ Mitigation Plan
Availability of hardware | 0.5 | Medium | Schedule | 
Exposure to customer code base | 0.5 | High | IP | Need to ensure NDA and training on IP protection.

## Slide 15: Key Success Factors and Best Practices adopted from Other Projects
  Key Success Factors
    Timely Communication And Escalation.
    Efficient and Optimized Code
    On Time Delivery
  Best Practices adapted
    Usage of Knowledge Repository
    Tool usage such as SVN, Clang
    Code Review – Review by peers at GES
    Project Tracking using Software Project Plan
    Weekly Status Reports
    100% compliance with time sheet filing
    QA Process- CMM Level 5/Level 3
    Weekly Team Meetings