## Sheet1
SI no	Date	Project	Actual Plan	What activities going to complete	Completed Activities	Pending Activities	Issues
1	12/04/18	touch_screen driver	Reading documentation, understanding it.	Reading documentation of touch driver and try to understand it.	Studied documentation but not completed.	Reading documentation
2	13/04/18	touch_screen driver	Reading data sheet of device and gather the required information from that.	Reading documentation and data sheet of device. And gather the require device info.	Studied documentation and data sheet of FT5406. And i have understood some thing.	Nothing
3	16/04/18	touch_screen driver	Understanding the .c file and analyzing the code working flow.	Understanding the .c file and analyzing the code working flow.	Studied about input subsystem, DSI and calibratoin but not understood calibration and made touch screen driver documentation.	Understanding the .c file.
4	17/04/18	touch_screen driver	Understanding the .c file and analyzing the code working flow.	Understanding the .c file and analyzing the code working flow and remaining concepts.	Studied Gestures and hardware communication with applications through Gestures and host and few API's in .c file	Awareness on some used API's in .c file
5	18/04/18	touch_screen driver	Implementation of .c file	Understanding the .c file and and remaining/Pending Activities.	Analyzed all call back functions in .c file but awareness on few used API's are remaining.	Implementation of .c file
6	19/04/18	touch_screen driver	Implementation of .c file	Implementation of .c file	Have been Implementing of .c file	Implementation of .c file
7	20/04/18	touch_screen driver	Implementation of .c file	Implementation of .c file	Have been Implementing of .c file	Implementation of .c file
8	23/04/18	touch_screen driver	Testing .c file	Have been done implementation of .c file andi am going to test it.	Have given Explanation and studied data sheet.	Testing .c file
9	24/04/18	touch_screen driver	Testing .c file	preparing design documentation .	Studied device registers and modes and Made flow chart design diagram.	Testing .c file
10	25/04/18	touch_screen driver	Study device registers and mode info	Studying device registers and mode info.	Studied device data sheet and found irq(INT) pin number and i have been implementing interrupt handler.	Implementation of .c file
11	26/04/18	touch_screen driver	Implementation of interrupt handler	Implementing interrupt handler	Implemented interrupt function but the interrupt raise is not happening.	Fixing issues in interrupt handler.
12	27/04/18	touch_screen driver	Study Raspberry pi data sheet , DSI pin configuration, GPU, about ribbon cable lines and about Interrupt line of touch screen on Raspberry pi 3.	Study Raspberry pi data sheet , DSI pin configuration, GPU, about ribbon cable lines and about Interrupt line of touch screen on Raspberry pi 3.	Have been Studied Raspberry pi data sheet , DSI pin configuration, about ribbon cable lines and about Interrupt line of touch screen on Raspberry pi 3.	GPU
13	30/04/18	touch_screen driver	Study GPU	Study GPU	Studied GPU concept on raspberry pi environment.	GPU
14	02/05/18	touch_screen driver	Study implementation of FT5406 driver from patch.	Study implementation of FT5406 driver from patch.	Studied implementation of FT5406 driver from patch.	Nothing
15	03/05/18	touch_screen driver	Prepare a Design Documentation.	Prepare a Design Documentation.	Have been made documentation of FT5406DQ9 driver	Nothing
16	04/05/18	touch_screen driver	Study touch screen driver on Raspberry PI 3	Study touch screen driver on Raspberry PI 3	Have been studied touch screen driver with GPU on Raspberry PI 3 and analyzed FT5406DQ9 driver.	Nothing